## DBU
Contract ID | Project ID | BU MGR ID | Project Name | Contract Start Date | Contract End Date | Expected Close Date | Your Comments | Remarks
90-0829 | 90-0829-20 | 160 | King Khalid University- Instal | 2015-01-01 | 2015-04-01 | 2015-08-31 | closed | Document for closing sent before
90-0829 | 90-0829-00 | 160 | King Khalid University- Overhe | 2015-01-01 | 2015-04-01 | 2015-08-31 | closed | Document for closing sent before
90-0832 | 90-0832-00 | 160 | Bisha & Shediq - Overhead | 2015-04-01 | 2015-07-31 | 2015-10-31 | Extend to 15-7-2016 | Matreial shortage delays starting the work
90-0832 | 90-0832-20 | 160 | Bisha & Shediq - Installation | 2015-04-01 | 2015-07-31 | 2015-10-31 | Extend to 15-7-2016 | Matreial shortage delays starting the work
90-0833 | 90-0833-00 | 160 | Bellasmer U/G - Overhead | 2015-04-01 | 2015-09-30 | 2015-12-31 | Extend to 15-6-2016 | Additional work received
90-0833 | 90-0833-20 | 160 | Bellasmer U/G- installation | 2015-04-01 | 2015-09-30 | 2015-12-31 | Extend to 15-6-2016 | Additional work received
90-0834 | 90-0834-00 | 160 | ALZORQ FEEDERS -Overhead | 2015-06-01 | 2015-08-31 | 2015-12-31 | Extend to 31-5-2016 | Matreial shortage delays starting the work
90-0834 | 90-0834-20 | 160 | ALZORQ FEEDERS -Installation | 2015-06-01 | 2015-08-31 | 2015-12-31 | Extend to 31-5-2016 | Matreial shortage delays starting the work
90-0902 | 90-0902-00 | 160 | OSP 2013 - Overhead | 2013-03-30 | 2014-11-30 | 2015-06-30 | closed | Document for closing sent before
90-0902 | 90-0902-20 | 160 | OSP 2013 - Generator | 2013-03-30 | 2014-11-30 | 2015-06-30 | closed | Document for closing sent before
90-0903 | 90-0903-00 | 160 | Replacement STC - Overhead | 2013-11-20 | 2015-11-20 | 2016-01-30 | closed | Document for closing sent before
90-0903 | 90-0903-20 | 160 | Replacement STC - Installation | 2013-11-20 | 2015-11-20 | 2016-01-30 | closed | Document for closing sent before
90-0983 | 90-0983-00 | 160 | Civil Work 2014 - Over Head | 2014-01-01 | 2014-12-31 | 2015-08-31 | closed | Document for closing sent before
90-0983 | 90-0983-20 | 160 | Civil Work 2014 - Installation | 2014-01-01 | 2014-12-31 | 2015-08-31 | closed | Document for closing sent before
90-1010 | 90-1010-00 | 160 | Mobily Riyadh - Overhead | 2012-04-02 | 2014-04-03 | 2015-06-30 | closed | Document for closing sent before
90-1010 | 90-1010-20 | 160 | Mobily Riyadh - Installation | 2012-04-02 | 2014-04-03 | 2015-06-30 | closed | Document for closing sent before
90-1101 | 90-1101-00 | 160 | Zain - Over Head | 2013-07-31 | 2014-07-31 | 2015-07-31 | on hold | Remaining to issue the ATS for Zain this week will be issued then we can close
90-1101 | 90-1101-20 | 160 | Zain - Installation | 2013-07-31 | 2014-07-31 | 2015-07-31 | on hold | Remaining to issue the ATS for Zain this week will be issued then we can close
90-0100 | 90-0100-00 | 160 | Assir Region Unified Contract | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0100 | 90-0101-20 | 160 | Asphalt Unit | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0100 | 90-0110-20 | 160 | Khamis & Ahad Rufaidah Unit | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0100 | 90-0115-20 | 160 | Abha Unit | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0100 | 90-0120-20 | 160 | Ballasmer Unit | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0100 | 90-0125-20 | 160 | Tareeb Unit | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0100 | 90-0130-20 | 160 | Tathlith Unit | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0100 | 90-0135-20 | 160 | Sarat Obidah Unit | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0100 | 90-0140-20 | 160 | Al-Magardah Unit | 2008-02-01 | 2013-02-28 | 2014-08-30 | closed
90-0400 | 90-0400-00 | 160 | Assir Maintenance Office | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold
90-0400 | 90-0410-20 | 160 | Abha Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0400 | 90-0415-20 | 160 | Khamis Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0400 | 90-0420-20 | 160 | Ahad Rufaidah Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0400 | 90-0430-20 | 160 | Ballasmer Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0400 | 90-0435-20 | 160 | Bisha Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0400 | 90-0440-20 | 160 | Al-Namas Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0400 | 90-0445-20 | 160 | Al Alaya Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0400 | 90-0450-20 | 160 | Tathlith Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0400 | 90-0455-20 | 160 | Tareeb Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | on hold | waiting PAC
90-0500 | 90-0500-00 | 160 | Jizan Maintenance Office | 2010-10-01 | 2013-06-30 | 2015-12-30 | closed
90-0500 | 90-0510-20 | 160 | Jizan Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | closed
90-0500 | 90-0515-20 | 160 | Sabia Maintenance old | 2010-10-01 | 2013-06-30 | 2015-12-30 | closed
90-0500 | 90-0520-20 | 160 | Samtah & Al-Khashle Maintenanc | 2010-10-01 | 2013-06-30 | 2015-12-30 | closed
90-0500 | 90-0525-20 | 160 | Abo Arish Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | closed
90-0500 | 90-0530-20 | 160 | Farasan Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | closed
90-0500 | 90-0560-20 | 160 | Emergency Group Maintenance | 2010-10-01 | 2013-06-30 | 2015-12-30 | closed
90-0500 | 90-0570-20 | 160 | Frasan Generators Maintanance | 2010-10-01 | 2013-06-30 | 2015-12-30 | closed
90-0602 | 90-0602-00 | 160 | Upgrade Power KFAB2 - Overhead | 2013-04-05 | 2014-04-12 | 2015-07-25 | on hold | waiting for subcontractor final payment
90-0602 | 90-0602-20 | 160 | Upgrade Power KFAB2 - Installation | 2013-04-05 | 2014-04-12 | 2015-07-25 | on hold | waiting for subcontractor final payment
90-0606 | 90-0606-00 | 160 | Abo Hajar - Overhead | 2012-08-01 | 2013-04-01 | 2015-07-25 | extened till 30/5/2016 | waiting for receiving final payment and subcontarctor final payment
90-0606 | 90-0606-10 | 160 | Abo Hajar - Procurment | 2012-08-01 | 2013-04-01 | 2015-07-25 | extened till 30/5/2017 | waiting for receiving final payment and subcontarctor final payment
90-0606 | 90-0606-15 | 160 | Abo Hajar - Civil Works | 2012-08-01 | 2013-04-01 | 2015-07-25 | waiting PAC | waiting for receiving final payment and subcontarctor final payment
90-0606 | 90-0606-20 | 160 | Abo Hajar - Installation | 2012-08-01 | 2013-04-01 | 2015-07-25 | waiting PAC | waiting receiving final payment and subcontarctor final payment
90-0617 | 90-0617-00 | 160 | Transformers Replac KFMMC - Ove | 2012-08-10 | 2013-08-10 | 2015-11-30 | extened till 31/11/2016 | - Delay in the project execution because of subcontractor & Client
90-0617 | 90-0617-20 | 160 | Transformers Replac KFMMC - Ins | 2012-08-10 | 2013-08-10 | 2015-11-30 | extened till 31/11/2017 | - Delay in the project execution because of subcontractor & Client
90-0618 | 90-0618-00 | 160 | Military Industries - Overhead | 2012-08-07 | 2015-02-20 | 2016-02-20 | on hold | waiting receiving final payment and subcontarctor final payment
90-0618 | 90-0618-20 | 160 | Military Industries - Install. | 2012-08-07 | 2015-02-20 | 2016-02-20 | on hold | waiting receiving final payment and subcontarctor final payment
90-0623 | 90-0623-00 | 160 | Royal Air Force Jabal AlWasl - Overhead | 2013-01-10 | 2014-01-10 | 2015-07-25 | on hold | waiting to receive the final payment
90-0623 | 90-0623-20 | 160 | Royal Air Force Jabal AlWasl- Installation | 2013-01-10 | 2014-01-10 | 2015-07-25 | on hold | waiting to receive the final payment
90-0633 | 90-0633-00 | 160 | Over Head Line Aramco - Over H | 2014-04-01 | 2015-03-31 | 2015-09-30 | Extend till 30/9/2016 | delay due to material shortage and manual excavation
90-0633 | 90-0633-20 | 160 | Over Head Line Aramco - Instal | 2014-04-01 | 2015-03-31 | 2015-09-30 | Extend till 30/9/2016 | delay due to material shortage and manual excavation
90-0636 | 90-0636-00 | 160 | Abha Altaif Shifting -Overhead | 2014-05-21 | 2014-09-20 | 2015-07-30 | Extend to 30-6-2016 | waiting for material balance and receiving final payment
90-0636 | 90-0636-20 | 160 | Abha Altaif Shifting -Installa | 2014-05-21 | 2014-09-20 | 2015-07-30 | Extend to 30-6-2016 | waiting for material balance and receiving final payment
90-0813 | 90-0813-00 | 160 | Al-Khaldia LT Calbe - Overhead | 2013-09-01 | 2014-01-31 | 2015-02-28 | closed
90-0813 | 90-0813-20 | 160 | Al-Khaldia LT - Installation | 2013-09-01 | 2014-01-31 | 2015-02-28 | closed
90-0819 | 90-0819-00 | 160 | Al Namas Feeders - Overhead | 2013-12-01 | 2014-05-31 | 2015-05-31 | closed
90-0819 | 90-0819-20 | 160 | Al Namas Feeders-Installation | 2013-12-01 | 2014-05-31 | 2015-05-31 | closed
90-0823 | 90-0823-00 | 160 | Baladya Street Cables-Overhead | 2014-08-01 | 2014-11-30 | 2015-03-31 | closed
90-0823 | 90-0823-20 | 160 | Baladya Street Cables-Installa | 2014-08-01 | 2014-11-30 | 2015-03-31 | closed
90-0824 | 90-0824-00 | 160 | Tandaha Cable - Overhead | 2014-10-25 | 2015-02-25 | 2015-05-31 | closed
90-0824 | 90-0824-20 | 160 | Tandaha Cable - Installation | 2014-10-25 | 2015-02-25 | 2015-05-31 | closed
90-0826 | 90-0826-00 | 160 | Tandaha Cable Part2 - Overhead | 2014-11-20 | 2015-03-20 | 2015-06-30 | Extend to 31-5-2016 | Work stopped due to military reason
90-0826 | 90-0826-20 | 160 | Tandaha Cable Part2 - Installa | 2014-11-20 | 2015-03-20 | 2015-06-30 | Extend to 31-5-2016 | Work stopped due to military reason
90-0827 | 90-0827-00 | 160 | Al-Alaya Hospital -Overhead | 2015-01-01 | 2015-05-31 | 2015-08-31 | closed
90-0827 | 90-0827-20 | 160 | Al-Alaya Hospital - Installati | 2015-01-01 | 2015-05-31 | 2015-08-31 | closed
90-0828 | 90-0828-00 | 160 | Almarai Cable - Overhead | 2015-01-01 | 2015-03-01 | 2015-06-30 | closed
90-0828 | 90-0828-20 | 160 | Almarai Cable - Installation | 2015-01-01 | 2015-03-01 | 2015-06-30 | closed

## Sheet1
Contract ID | Project ID | BU MGR ID | Project Name | Contract Start Date | Contract End Date | Expected Close Date | Your Comments
80-0101 | 80-0101-00 | 3563 | Con.Tathleeth - Overhead | 41034 | 41669 | 42399
80-0101 | 80-0101-01 | 3563 | Con.Tathleeth - Design | 41034 | 41669 | 42399
80-0101 | 80-0101-05 | 3563 | Con.Tathleeth - Mobilization | 41034 | 41669 | 42399
80-0101 | 80-0101-10 | 3563 | Con.Tathleeth - Procurment | 41034 | 41669 | 42399
80-0101 | 80-0101-15 | 3563 | Con.Tathleeth - Civil Works | 41034 | 41669 | 42399
80-0101 | 80-0101-20 | 3563 | Con.Tathleeth - Installation | 41034 | 41669 | 42399
80-0101 | 80-0101-25 | 3563 | Con.Tathleeth -Testing&Commis | 41034 | 41669 | 42399
80-0101 | 80-0101-30 | 3563 | Con.Tathleeth - Training | 41034 | 41669 | 42399
80-0101 | 80-0101-35 | 3563 | Con.Tathleeth - Closing Punch | 41034 | 41669 | 42399
80-0101 | 80-0101-51 | 3563 | Con. Bishatown - Design | 41034 | 41669 | 42399
80-0101 | 80-0101-55 | 3563 | Con. Bishatown - Mobilization | 41034 | 41669 | 42399
80-0101 | 80-0101-60 | 3563 | Con.Bishtown - Procurment | 41034 | 41669 | 42399
80-0101 | 80-0101-65 | 3563 | Con. Bishatown - Civil Works | 41034 | 41669 | 42399
80-0101 | 80-0101-70 | 3563 | Con. Bishatown - Installation | 41034 | 41669 | 42399
80-0101 | 80-0101-75 | 3563 | Con. Bishatown -Testing&Commis | 41034 | 41669 | 42399
80-0101 | 80-0101-80 | 3563 | Con. Bishatown - Training | 41034 | 41669 | 42399
80-0101 | 80-0101-85 | 3563 | Con.Bishatown - Closing Punch | 41034 | 41669 | 42399
80-0103 | 80-0103-00 | 3563 | Con. Siffah - Overhead | 41157 | 42093 | 42368
80-0103 | 80-0103-01 | 3563 | Con. Siffah - Design | 41157 | 42093 | 42368
80-0103 | 80-0103-05 | 3563 | Con. Siffah - Mobilization | 41157 | 42093 | 42368
80-0103 | 80-0103-10 | 3563 | Con. Siffah - Procurment | 41157 | 42093 | 42368
80-0103 | 80-0103-15 | 3563 | Con. Siffah - Civil Works | 41157 | 42093 | 42368
80-0103 | 80-0103-20 | 3563 | Con. Siffah - Installation | 41157 | 42093 | 42368
80-0103 | 80-0103-25 | 3563 | Con. Siffah - Testing&Commissi | 41157 | 42093 | 42368
80-0103 | 80-0103-30 | 3563 | Con. Siffah - Training | 41157 | 42093 | 42368
80-0103 | 80-0103-35 | 3563 | Con. Siffah - Closing Punch | 41157 | 42093 | 42368
80-0104 | 80-0104-00 | 3563 | Debaa 2 - Overhead | 40917 | 41744 | 42292
80-0104 | 80-0104-01 | 3563 | Debaa 2 - Design | 40917 | 41744 | 42292
80-0104 | 80-0104-05 | 3563 | Debaa 2 - Mobilization | 40917 | 41744 | 42292
80-0104 | 80-0104-10 | 3563 | Debaa 2 -Procurment | 40917 | 41744 | 42292
80-0104 | 80-0104-15 | 3563 | Debaa 2 -Civil Works | 40917 | 41744 | 42292
80-0104 | 80-0104-16 | 3563 | Tabouk 4 - Civil Works | 40917 | 41744 | 42292
80-0104 | 80-0104-20 | 3563 | Debaa 2 -Installation | 40917 | 41744 | 42292
80-0104 | 80-0104-21 | 3563 | Tabouk 4 -Installation | 40917 | 41744 | 42292
80-0104 | 80-0104-25 | 3563 | Debaa 2 -Testing & Commissioni | 40917 | 41744 | 42292
80-0104 | 80-0104-30 | 3563 | Debaa 2 -Training | 40917 | 41744 | 42292
80-0104 | 80-0104-35 | 3563 | Debaa 2 -Closing Punch List | 40917 | 41744 | 42292
80-0105 | 80-0105-00 | 3563 | Al Jamoom 2 - Overhead | 40917 | 41744 | 42231
80-0105 | 80-0105-01 | 3563 | Al Jamoom 2 - Design | 40917 | 41744 | 42231
80-0105 | 80-0105-05 | 3563 | Al Jamoom 2 - Mobilization | 40917 | 41744 | 42231
80-0105 | 80-0105-10 | 3563 | Al Jamoom 2 - Procurment | 40917 | 41744 | 42231
80-0105 | 80-0105-15 | 3563 | Al Jamoom 2 - Civil Works | 40917 | 41744 | 42231
80-0105 | 80-0105-20 | 3563 | Al Jamoom 2 - Installation | 40917 | 41744 | 42231
80-0105 | 80-0105-25 | 3563 | Al Jamoom 2 - Testing&Commissi | 40917 | 41744 | 42231
80-0105 | 80-0105-30 | 3563 | Al Jamoom 2 - Training | 40917 | 41744 | 42231
80-0105 | 80-0105-35 | 3563 | Al Jamoom 2 - Closing Punch | 40917 | 41744 | 42231
80-0106 | 80-0106-00 | 3563 | Al Rodaaf 2 - Overhead | 40917 | 41744 | 42368
80-0106 | 80-0106-01 | 3563 | Al Rodaaf 2 - Design | 40917 | 41744 | 42368
80-0106 | 80-0106-05 | 3563 | Al Rodaaf 2 - Mobilization | 40917 | 41744 | 42368
80-0106 | 80-0106-10 | 3563 | Al Rodaaf 2 - Procurment | 40917 | 41744 | 42368
80-0106 | 80-0106-15 | 3563 | Al Rodaaf 2 - Civil Works | 40917 | 41744 | 42368
80-0106 | 80-0106-20 | 3563 | Al Rodaaf 2 - Installation | 40917 | 41744 | 42368
80-0106 | 80-0106-25 | 3563 | Al Rodaaf 2 - Testing&Commissi | 40917 | 41744 | 42368
80-0106 | 80-0106-30 | 3563 | Al Rodaaf 2 - Training | 40917 | 41744 | 42368
80-0106 | 80-0106-35 | 3563 | Al Rodaaf 2 - Closing Punch | 40917 | 41744 | 42368
80-0107 | 80-0107-00 | 3563 | Ext. Khaibar - Overhead | 40917 | 41623 | 42246
80-0107 | 80-0107-01 | 3563 | Ext. Khaibar - Design | 40917 | 41623 | 42246
80-0107 | 80-0107-05 | 3563 | Ext. Khaibar - Mobilization | 40917 | 41623 | 42246
80-0107 | 80-0107-10 | 3563 | Ext. Khaibar - Procurment | 40917 | 41623 | 42246
80-0107 | 80-0107-15 | 3563 | Ext. Khaibar - Civil Works | 40917 | 41623 | 42246
80-0107 | 80-0107-20 | 3563 | Ext. Khaibar - Installation | 40917 | 41623 | 42246
80-0107 | 80-0107-25 | 3563 | Ext. Khaibar - Testing&Commiss | 40917 | 41623 | 42246
80-0107 | 80-0107-30 | 3563 | Ext. Khaibar - Training | 40917 | 41623 | 42246
80-0107 | 80-0107-35 | 3563 | Ext. Khaibar - Closing Punch | 40917 | 41623 | 42246
80-0108 | 80-0108-00 | 3563 | Ext. ICY - Overhead | 40917 | 41623 | 42368
80-0108 | 80-0108-01 | 3563 | Ext. ICY - Design | 40917 | 41623 | 42368
80-0108 | 80-0108-05 | 3563 | Ext. ICY - Mobilization & DeMo | 40917 | 41623 | 42368
80-0108 | 80-0108-10 | 3563 | Ext. ICY - Procurment | 40917 | 41623 | 42368
80-0108 | 80-0108-15 | 3563 | Ext. ICY - Civil Works | 40917 | 41623 | 42368
80-0108 | 80-0108-20 | 3563 | Ext. ICY - Installation | 40917 | 41623 | 42368
80-0108 | 80-0108-25 | 3563 | Ext. ICY - Testing & Commissi | 40917 | 41623 | 42368
80-0108 | 80-0108-30 | 3563 | Ext. ICY - Training | 40917 | 41623 | 42368
80-0108 | 80-0108-35 | 3563 | Ext. ICY - Closing Punch List | 40917 | 41623 | 42368
80-0109 | 80-0109-00 | 7305 | SAOO - Aramco - Overhead | 41304 | 42246 | 42246
80-0109 | 80-0109-01 | 7305 | SAOO - Aramco - Design | 41304 | 42246 | 42246
80-0109 | 80-0109-05 | 7305 | SAOO - Aramco - Mobilization | 41304 | 42246 | 42246
80-0109 | 80-0109-10 | 7305 | SAOO - Aramco - Procurement | 41304 | 42246 | 42246
80-0109 | 80-0109-15 | 7305 | SAOO - Aramco - Civil Works | 41304 | 42246 | 42246
80-0109 | 80-0109-20 | 7305 | SAOO - Aramco - Installation | 41304 | 42246 | 42246
80-0109 | 80-0109-25 | 7305 | SAOO - Aramco - Testing & Comm | 41304 | 42246 | 42246
80-0109 | 80-0109-35 | 7305 | SAOO - Aramco - Closing & Punc | 41304 | 42246 | 42246
80-0111 | 80-0111-00 | 3563 | Moabdah & Zahra - Overhead | 40932 | 42090 | 42368
80-0111 | 80-0111-01 | 3563 | Moabdah & Zahra - Design | 40932 | 42090 | 42368
80-0111 | 80-0111-05 | 3563 | Moabdah & Zahra - Mobilization | 40932 | 42090 | 42368
80-0111 | 80-0111-10 | 3563 | Moabdah & Zahra - Procurment | 40932 | 42090 | 42368
80-0111 | 80-0111-15 | 3563 | Moabdah & Zahra - Civil Works | 40932 | 42090 | 42368
80-0111 | 80-0111-20 | 3563 | Moabdah & Zahra -Installation | 40932 | 42090 | 42368
80-0111 | 80-0111-25 | 3563 | Moabdah & Zahra -Testing&Commi | 40932 | 42090 | 42368
80-0111 | 80-0111-30 | 3563 | Moabdah & Zahra - Training | 40932 | 42090 | 42368
80-0111 | 80-0111-35 | 3563 | Moabdah & Zahra -Closing Punch | 40932 | 42090 | 42368
80-0112 | 80-0112-00 | 3563 | Sports City - Overhead | 41286 | 41985 | 42368
80-0112 | 80-0112-01 | 3563 | Sports City - Design | 41286 | 41985 | 42368
80-0112 | 80-0112-05 | 3563 | Sports City - Mobilization & D | 41286 | 41985 | 42368
80-0112 | 80-0112-10 | 3563 | Sports City - Procurement | 41286 | 41985 | 42368
80-0112 | 80-0112-15 | 3563 | Sports City - Civil Works | 41286 | 41985 | 42368
80-0112 | 80-0112-20 | 3563 | Sports City - Installation | 41286 | 41985 | 42368
80-0112 | 80-0112-25 | 3563 | Sports City - Testing & Commis | 41286 | 41985 | 42368
80-0112 | 80-0112-30 | 3563 | Sports City - Training | 41286 | 41985 | 42368
80-0112 | 80-0112-35 | 3563 | Sports City - Closing & Punch | 41286 | 41985 | 42368
80-0113 | 80-0113-00 | 3563 | Tabouk11 - Overhead | 41395 | 42217 | 42401
80-0113 | 80-0113-01 | 3563 | Tabouk11 - Design | 41395 | 42217 | 42401
80-0113 | 80-0113-05 | 3563 | Tabouk11 - Mobilization | 41395 | 42217 | 42401
80-0113 | 80-0113-10 | 3563 | Tabouk11 - Procurment | 41395 | 42217 | 42401
80-0113 | 80-0113-15 | 3563 | Tabouk11 - Civil Works | 41395 | 42217 | 42401
80-0113 | 80-0113-20 | 3563 | Tabouk11 - Installation OH | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4215 | 3563 | Tabouk11- CABLE TRAY | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4243 | 3563 | Tabouk11- OUTDOOR Lighting | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4300 | 3563 | Tabouk11- ELECTRICAL Installat | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4301 | 3563 | Tabouk11- HV GIS | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4310 | 3563 | Tabouk11- SAS | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4311 | 3563 | Tabouk11- TELECOMUNICATION | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4312 | 3563 | Tabouk11- NER | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4313 | 3563 | Tabouk11- LIGHTNING | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4320 | 3563 | Tabouk11- SWITCH GEAR | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4330 | 3563 | Tabouk11- POWER TRANSFOMER | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4340 | 3563 | Tabouk11- CAPACITOR BANK | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4351 | 3563 | Tabouk11- HV POWER CABLES | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4352 | 3563 | Tabouk11- MV POWER CABLES | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4353 | 3563 | Tabouk11- LV CABLES | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4354 | 3563 | Tabouk11- FOC & CONTROL CABLES | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4360 | 3563 | Tabouk11- AUXILIARY TRANSF | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4370 | 3563 | Tabouk11- ACDB/DCDB PANELS | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4380 | 3563 | Tabouk11- BATTERY DC AUX | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4390 | 3563 | Tabouk11- CONTROL & PROTECTION | 41395 | 42217 | 42401
80-0113 | 80-0113-20-4420 | 3563 | Tabouk11- REMOTE CONNECTION | 41395 | 42217 | 42401
80-0113 | 80-0113-20-6000 | 3563 | Tabouk11- Demobilization | 41395 | 42217 | 42401
80-0113 | 80-0113-25 | 3563 | Tabouk11 - Testing&Comm | 41395 | 42217 | 42401
80-0113 | 80-0113-35 | 3563 | Tabouk11 - Closing Punch List | 41395 | 42217 | 42401
80-0118 | 80-0118-00 | 3563 | Motamrat - Overhead | 41612 | 42404 | 42404
80-0118 | 80-0118-01 | 3563 | Motamrat - Design | 41612 | 42404 | 42404
80-0118 | 80-0118-05 | 3563 | Motamrat - Mobilization | 41612 | 42404 | 42404
80-0118 | 80-0118-10 | 3563 | Motamrat - Procurment | 41612 | 42404 | 42404
80-0118 | 80-0118-15 | 3563 | Motamrat - Civil Works Over H | 41612 | 42404 | 42404
80-0118 | 80-0118-20 | 3563 | Motamrat - Installation | 41612 | 42404 | 42404
80-0118 | 80-0118-20-1000 | 3563 | Install-1000 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-1010 | 3563 | Install-1010 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-4641 | 3563 | Install-4641 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5081 | 3563 | Install-5081 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5091 | 3563 | Install-5091 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5171 | 3563 | Install-5171 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5251 | 3563 | Install-5251 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5321 | 3563 | Install-5321 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5331 | 3563 | Install-5331 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5381 | 3563 | Install-5381 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5451 | 3563 | Install-5451 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5491 | 3563 | Install-5491 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5521 | 3563 | Install-5521 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5531 | 3563 | Install-5531 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5541 | 3563 | Install-5541 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5551 | 3563 | Install-5551 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5571 | 3563 | Install-5571 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5591 | 3563 | Install-5591 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5601 | 3563 | Install-5601 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5621 | 3563 | Install-5621 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5641 | 3563 | Install-5641 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5661 | 3563 | Install-5661 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5671 | 3563 | Install-5671 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5681 | 3563 | Install-5681 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5711 | 3563 | Install-5711 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5721 | 3563 | Install-5721 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5731 | 3563 | Install-5731 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5751 | 3563 | Install-5751 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-5761 | 3563 | Install-5761 | 41612 | 42404 | 42404
80-0118 | 80-0118-20-6961 | 3563 | Install-6961 | 41612 | 42404 | 42404
80-0118 | 80-0118-25 | 3563 | Motamrat - Testing & Commiss | 41612 | 42404 | 42404
80-0118 | 80-0118-30 | 3563 | Motamrat - Training | 41612 | 42404 | 42404
80-0118 | 80-0118-35 | 3563 | Motamrat - Closing Punch | 41612 | 42404 | 42404
80-0119 | 80-0119-00 | 3563 | Gulf Salman - Overhead | 41609 | 42404 | 42404
80-0119 | 80-0119-01 | 3563 | Gulf Salman - Design | 41609 | 42404 | 42404
80-0119 | 80-0119-05 | 3563 | Gulf Salman - Mobilization | 41609 | 42404 | 42404
80-0119 | 80-0119-10 | 3563 | Gulf Salman - Procurment | 41609 | 42404 | 42404
80-0119 | 80-0119-15 | 3563 | Gulf Salman-Civil Works Over H | 41609 | 42404 | 42404
80-0119 | 80-0119-20 | 3563 | Gulf Salman - Installation | 41609 | 42404 | 42404
80-0119 | 80-0119-20-1000 | 3563 | Install-1000 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3530 | 3563 | Install-3530 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3540 | 3563 | Install-3540 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3550 | 3563 | Install-3550 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3560 | 3563 | Install-3560 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3570 | 3563 | Install-3570 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3580 | 3563 | Install-3580 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3590 | 3563 | Install-3590 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3600 | 3563 | Install-3600 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3610 | 3563 | Install-3610 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3620 | 3563 | Install-3620 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3630 | 3563 | Install-3630 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3640 | 3563 | Install-3640 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3650 | 3563 | Install-3650 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3660 | 3563 | Install-3660 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3670 | 3563 | Install-3670 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3680 | 3563 | Install-3680 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3690 | 3563 | Install-3690 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3700 | 3563 | Install-3700 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3710 | 3563 | Install-3710 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3720 | 3563 | Install-3720 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3730 | 3563 | Install-3730 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3740 | 3563 | Install-3740 | 41609 | 42404 | 42404
80-0119 | 80-0119-20-3760 | 3563 | Install-3760 | 41609 | 42404 | 42404
80-0119 | 80-0119-25 | 3563 | Gulf Salman -Testing & Commiss | 41609 | 42404 | 42404
80-0119 | 80-0119-30 | 3563 | Gulf Salman - Training | 41609 | 42404 | 42404
80-0119 | 80-0119-35 | 3563 | Gulf Salman - Closing Punch | 41609 | 42404 | 42404
80-0122 | 80-0122-00 | 3563 | Cumber Land - Over Head | 41716 | 41776 | 42368
80-0122 | 80-0122-20 | 3563 | Cumber Land - Installation | 41716 | 41776 | 42368
80-0131 | 80-0131-00 | 3563 | King Faisal Hospital-Overhead | 41981 | 42416 | 42416
80-0131 | 80-0131-01 | 3563 | King Faisal Hospital-Design | 41981 | 42416 | 42416
80-0131 | 80-0131-05 | 3563 | King Faisal Hospital-Mobilliza | 41981 | 42416 | 42416
80-0131 | 80-0131-10 | 3563 | King Faisal Hospital-Procureme | 41981 | 42416 | 42416
80-0131 | 80-0131-15 | 3563 | King Faisal Hospital-Civil Wor | 41981 | 42416 | 42416
80-0131 | 80-0131-20 | 3563 | King Faisal Hospital-Installat | 41981 | 42416 | 42416
80-0131 | 80-0131-20-215 | 3563 | KFH.2.4.2.15 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-31 | 3563 | KFH.2.4.3.1 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-310 | 3563 | KFH.2.4.3.10 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-311 | 3563 | KFH.2.4.3.11 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-312 | 3563 | KFH.2.4.3.12 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-313 | 3563 | KFH.2.4.3.13 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-32 | 3563 | KFH.2.4.3.2 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-33 | 3563 | KFH.2.4.3.3 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-34 | 3563 | KFH.2.4.3.4 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-351 | 3563 | KFH.2.4.3.5.1 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-352 | 3563 | KFH.2.4.3.5.2 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-353 | 3563 | KFH.2.4.3.5.3 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-354 | 3563 | KFH.2.4.3.5.4 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-36 | 3563 | KFH.2.4.3.6 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-37 | 3563 | KFH.2.4.3.7 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-38 | 3563 | KFH.2.4.3.8 | 41981 | 42416 | 42416
80-0131 | 80-0131-20-39 | 3563 | KFH.2.4.3.9 | 41981 | 42416 | 42416
80-0131 | 80-0131-25 | 3563 | King Faisal Hospital-Testing | 41981 | 42416 | 42416
80-0131 | 80-0131-30 | 3563 | King Faisal Hospital-Training | 41981 | 42416 | 42416
80-0131 | 80-0131-35 | 3563 | King Faisal Hospital-Closing P | 41981 | 42416 | 42416
80-0175 | 80-0175-00 | 3563 | Tabouk 10 - Overhead | 40310 | 41591 | 42155
80-0175 | 80-0175-01 | 3563 | Tabouk 10 - Design | 40310 | 41591 | 42155
80-0175 | 80-0175-05 | 3563 | Tabouk 10 - Mobilization | 40310 | 41591 | 42155
80-0175 | 80-0175-10 | 3563 | Tabouk 10 - Procurment | 40310 | 41591 | 42155
80-0175 | 80-0175-15 | 3563 | Tabouk 10 - Civil Works | 40310 | 41591 | 42155
80-0175 | 80-0175-20 | 3563 | Tabouk 10 - Installation | 40310 | 41591 | 42155
80-0175 | 80-0175-25 | 3563 | Tabouk 10 - Testing & Commissi | 40310 | 41591 | 42155
80-0175 | 80-0175-30 | 3563 | Tabouk 10 - Training | 40310 | 41591 | 42155
80-0175 | 80-0175-35 | 3563 | Tabouk 10 - Closing Punch | 40310 | 41591 | 42155
80-0195 | 80-0195-00 | 3563 | Tabouk University - Overhead | 40548 | 41279 | 42368
80-0195 | 80-0195-01 | 3563 | Tabouk University - Design | 40548 | 41279 | 42368
80-0195 | 80-0195-05 | 3563 | Tabouk University-Mobilization | 40548 | 41279 | 42368
80-0195 | 80-0195-10 | 3563 | Tabouk University - Procurment | 40548 | 41279 | 42368
80-0195 | 80-0195-15 | 3563 | Tabouk University -Civil Works | 40548 | 41279 | 42368
80-0195 | 80-0195-20 | 3563 | Tabouk University-Installation | 40548 | 41279 | 42368
80-0195 | 80-0195-25 | 3563 | Tabouk University-Testing&Comm | 40548 | 41279 | 42368
80-0195 | 80-0195-30 | 3563 | Tabouk University - Training | 40548 | 41279 | 42368
80-0195 | 80-0195-35 | 3563 | Tabouk Universi -Closing Punch | 40548 | 41279 | 42368
80-0570 | 80-0570-00 | 3563 | Baljurashi North - Overhead | 39067 | 40997 | 42307
80-0570 | 80-0570-01 | 3563 | Baljurashi North - Design | 39067 | 40997 | 42307
80-0570 | 80-0570-05 | 3563 | Baljurashi North -Mobilization | 39067 | 40997 | 42307
80-0570 | 80-0570-10 | 3563 | Baljurashi North - Procurment | 39067 | 40997 | 42307
80-0570 | 80-0570-15 | 3563 | Baljurashi North - Civil Works | 39067 | 40997 | 42307
80-0570 | 80-0570-20 | 3563 | Baljurashi North-Installation | 39067 | 40997 | 42307
80-0570 | 80-0570-25 | 3563 | Baljurashi North - esting&Comm | 39067 | 40997 | 42307
80-0570 | 80-0570-30 | 3563 | Baljurashi North - Training | 39067 | 40997 | 42307
80-0570 | 80-0570-35 | 3563 | Baljurashi North-Closing Punch | 39067 | 40997 | 42307
80-0575 | 80-0575-00 | 3563 | KKAB - Overhead | 38822 | 39522 | 42003
80-0575 | 80-0575-01 | 3563 | KKAB - Design | 38822 | 39522 | 42003
80-0575 | 80-0575-05 | 3563 | KKAB - Mobilization | 38822 | 39522 | 42003
80-0575 | 80-0575-10 | 3563 | KKAB - Procurment | 38822 | 39522 | 42003
80-0575 | 80-0575-15 | 3563 | KKAB - Civil Works | 38822 | 39522 | 42003
80-0575 | 80-0575-20 | 3563 | KKAB - Installation | 38822 | 39522 | 42003
80-0575 | 80-0575-25 | 3563 | KKAB - Testing & Commissi | 38822 | 39522 | 42003
80-0575 | 80-0575-30 | 3563 | KKAB - Training | 38822 | 39522 | 42003
80-0575 | 80-0575-35 | 3563 | KKAB - Closing Punch | 38822 | 39522 | 42003
80-0585 | 80-0585-00 | 3563 | SWCC - Overhead | 40033 | 41577 | 42338
80-0585 | 80-0585-KH-00 | 3563 | SWCC Khamis Office | 40033 | 41577 | 42338
80-0585 | 80-0585-MR-00 | 3563 | SWCC Magarda Office | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA2-01 | 3563 | SWCC - PSA2 - Design | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA2-05 | 3563 | SWCC - PSA2 - Mobilization | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA2-10 | 3563 | SWCC - PSA2 - Procurment | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA2-15 | 3563 | SWCC - PSA2 - Civil Works | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA2-20 | 3563 | SWCC - PSA2 - Installation | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA2-25 | 3563 | SWCC - PSA2 - Testing&Commissi | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA2-30 | 3563 | SWCC - PSA2 - Training | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA2-35 | 3563 | SWCC - PSA2 - Closing Punch | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA3-01 | 3563 | SWCC - PSA3 - Design | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA3-05 | 3563 | SWCC - PSA3 - Mobilization | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA3-10 | 3563 | SWCC - PSA3 - Procurment | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA3-15 | 3563 | SWCC - PSA3 - Civil Works | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA3-20 | 3563 | SWCC - PSA3 - Installation | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA3-25 | 3563 | SWCC - PSA3 - Testing&Commissi | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA3-30 | 3563 | SWCC - PSA3 - Training | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA3-35 | 3563 | SWCC - PSA3 - Closing Punch | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA4-01 | 3563 | SWCC - PSA4 - Design | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA4-05 | 3563 | SWCC - PSA4 - Mobilization | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA4-10 | 3563 | SWCC - PSA4 - Procurment | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA4-15 | 3563 | SWCC - PSA4 - Civil Works | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA4-20 | 3563 | SWCC - PSA4 - Installation | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA4-25 | 3563 | SWCC - PSA4 - Testing&Commissi | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA4-30 | 3563 | SWCC - PSA4 - Training | 40033 | 41577 | 42338
80-0585 | 80-0585-PSA4-35 | 3563 | SWCC - PSA4 - Closing Punch | 40033 | 41577 | 42338
80-0585 | 80-0585-PSDJ-01 | 3563 | SWCC - PSDJ - Design | 40033 | 41577 | 42338
80-0585 | 80-0585-PSDJ-05 | 3563 | SWCC - PSDJ - Mobilization | 40033 | 41577 | 42338
80-0585 | 80-0585-PSDJ-10 | 3563 | SWCC - PSDJ - Procurment | 40033 | 41577 | 42338
80-0585 | 80-0585-PSDJ-15 | 3563 | SWCC - PSDJ - Civil Works | 40033 | 41577 | 42338
80-0585 | 80-0585-PSDJ-20 | 3563 | SWCC - PSDJ - Installation | 40033 | 41577 | 42338
80-0585 | 80-0585-PSDJ-25 | 3563 | SWCC - PSDJ - Testing&Commissi | 40033 | 41577 | 42338
80-0585 | 80-0585-PSDJ-30 | 3563 | SWCC - PSDJ - Training | 40033 | 41577 | 42338
80-0585 | 80-0585-PSDJ-35 | 3563 | SWCC - PSDJ - Closing Punch | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR1-01 | 3563 | SWCC - PSR1 - Design | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR1-05 | 3563 | SWCC - PSR1 - Mobilization | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR1-10 | 3563 | SWCC - PSR1 - Procurment | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR1-15 | 3563 | SWCC - PSR1 - Civil Works | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR1-20 | 3563 | SWCC - PSR1 - Installation | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR1-25 | 3563 | SWCC - PSR1 - Testing&Commissi | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR1-30 | 3563 | SWCC - PSR1 - Training | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR1-35 | 3563 | SWCC - PSR1 - Closing Punch | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR2-01 | 3563 | SWCC - PSR2 - Design | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR2-05 | 3563 | SWCC - PSR2 - Mobilization | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR2-10 | 3563 | SWCC - PSR2 - Procurment | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR2-15 | 3563 | SWCC - PSR2 - Civil Works | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR2-20 | 3563 | SWCC - PSR2 - Installation | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR2-25 | 3563 | SWCC - PSR2 - Testing&Commissi | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR2-30 | 3563 | SWCC - PSR2 - Training | 40033 | 41577 | 42338
80-0585 | 80-0585-PSR2-35 | 3563 | SWCC - PSR2 - Closing Punch | 40033 | 41577 | 42338
80-0615 | 80-0615-00 | 3563 | Iskan Al Hisma - Overhead | 40635 | 41334 | 42369
80-0615 | 80-0615-01 | 3563 | Iskan Al Hisma - Design | 40635 | 41334 | 42369
80-0615 | 80-0615-05 | 3563 | Iskan Al Hisma - Mobilization | 40635 | 41334 | 42369
80-0615 | 80-0615-10 | 3563 | Iskan Al Hisma - Procurment | 40635 | 41334 | 42369
80-0615 | 80-0615-15 | 3563 | Iskan Al Hisma - Civil Works | 40635 | 41334 | 42369
80-0615 | 80-0615-20 | 3563 | Iskan Al Hisma - Installation | 40635 | 41334 | 42369
80-0615 | 80-0615-25 | 3563 | Iskan Al Hisma - Testing&Comm | 40635 | 41334 | 42369
80-0615 | 80-0615-30 | 3563 | Iskan Al Hisma - Training | 40635 | 41334 | 42369
80-0615 | 80-0615-35 | 3563 | Iskan Al Hisma - Closing Punch | 40635 | 41334 | 42369
83-0011 | 83-0011-00 | 160 | HV Circuit 8040-8117 -Overhead | 42148 | 42178 | 42216
83-0011 | 83-0011-20 | 160 | HV Circuit 8040-8117 -Installa | 42148 | 42178 | 42216
83-0101 | 83-0101-00 | 160 | 132KV Cables Tabouk-Overhead | 41315 | 41614 | 41796
83-0101 | 83-0101-20 | 160 | 132KV Cables Tabouk-Installati | 41315 | 41614 | 41796
83-0102 | 83-0102-00 | 160 | Cable Sealing S/S 8705 -Overhe | 42115 | 42175 | 42216
83-0102 | 83-0102-20 | 160 | Cable Sealing S/S 8705 -Instal | 42115 | 42175 | 42216
84-0100 | 84-0100-00 | 6963 | Solar Energy Development | 41347 | 41895 | 41898
85-0013 | 85-0013-35 | 7073 | Rent engineer For SEP Projects | 42125 | 42156 | 42156
85-0014 | 85-0014-35 | 7073 | Construction N Aziziah 3 S/S | 42176 | 42183 | 42183
85-0102 | 85-0102-35 | 7073 | Testing Sharurah PP1 | 41456 | 41759 | 42154
85-0102 | 85-0102-75 | 7073 | Testing Sharurah PP2 | 41456 | 41759 | 42154
85-0103 | 85-0103-35 | 7073 | Testing Eshar Siffah 132/33 KV | 41730 | 41943 | 42170
85-0104 | 85-0104-35 | 7073 | Testing Debaah 2 | 41570 | 41912 | 42155
85-0111 | 85-0111-35 | 7073 | Testing Moabdah S/S 110/13.8KV | 41730 | 41881 | 42109
85-0113 | 85-0113-36 | 7073 | Testing Of Tabouk 11 | 41980 | 41986 | 42200
85-0113 | 85-0113-35 | 7073 | Testing Of Tabouk 11 | 41980 | 41986 | 42200
85-0113 | 85-0113-37 | 7073 | Testing Of Tabouk 11 | 41980 | 41986 | 42200
85-0114 | 85-0114-35 | 7073 | Testing Al-Barakah S/S | 41944 | 42185 | 42277
85-0114 | 85-0114-36 | 7073 | Testing Al-Barakah S/S | 41944 | 42185 | 42277
85-0114 | 85-0114-37 | 7073 | Testing Al Barakah S/S | 41944 | 42185 | 42277
85-0116 | 85-0116-35 | 7073 | Al-Mashaar S/S-Renting Enginee | 42064 | 42125 | 42125
85-0118 | 85-0118-35 | 7073 | Al-Motmarat S/S Testing | 42064 | 42278 | 42308
85-0119 | 85-0119-35 | 7073 | Gulf Salman S/S Testing | 42064 | 42278 | 42308
85-0121 | 85-0121-35 | 7073 | Ruffaidah & Suffa -GESCO | 42180 | 42210 | 42241
85-0131 | 85-0131-25 | 7073 | KFH GIS 110/13.8 H.V Test & PD | 42292 | 42317 | 24:00
85-0131 | 85-0131-26 | 7073 | KFH H.V Test for XLPE Transfor | 42292 | 42317 | 24:00
85-0615 | 85-0615-35 | 7073 | HV Test for 33KV Bus Bar ISKAN | 41629 | 41633 | 42185
85-0615 | 85-0615-40 | 7073 | Iskan AlHisma S/S and Remote | 41629 | 41633 | 42185
85-0618 | 85-0618-35 | 7073 | Military Factories Project | 42009 | 42097 | 42155
85-1003 | 85-1003-35 | 7073 | Replacment of 13.8KV Shunt | 41059 | 42217 | 42308
85-1004 | 85-1004-35 | 7073 | Installation Tabouk,Duba | 41059 | 42240 | 42369
85-1008 | 85-1008-35 | 7073 | Jamoom - Testing & Commission | 42249 | 42264 | 42264
85-1009 | 85-1009-25 | 7073 | Discharge measuring test | 42259 | 42262 | 42262
85-1010 | 85-1010-25 | 7073 | Testing & Commissioning | 42311 | 42403 | 42403
86-0112 | 86-0112-15 | 3563 | King Abdullah Sport City | 41364 | 42035 | 42369
88-0010 | 88-0010-00 | 3563 | Management / Head Office | 42005 | 24:00 | 24:00
90-0100 | 90-0100-00 | 160 | Assir Region Unified Contract | 39479 | 41333 | 2014-08-30
90-0100 | 90-0101-20 | 160 | Asphalt Unit | 39479 | 41333 | 2014-08-30
90-0100 | 90-0110-20 | 160 | Khamis & Ahad Rufaidah Unit | 39479 | 41333 | 2014-08-30
90-0100 | 90-0115-20 | 160 | Abha Unit | 39479 | 2013-02-28 | 2014-08-30
90-0100 | 90-0120-20 | 160 | Ballasmer Unit | 39479 | 41333 | 41881
90-0100 | 90-0125-20 | 160 | Tareeb Unit | 2008-02-01 | 41333 | 41881
90-0100 | 90-0130-20 | 160 | Tathlith Unit | 2008-02-01 | 41333 | 41881
90-0100 | 90-0135-20 | 160 | Sarat Obidah Unit | 2008-02-01 | 41333 | 41881
90-0100 | 90-0140-20 | 160 | Al-Magardah Unit | 39479 | 41333 | 41881
90-0400 | 90-0400-00 | 160 | Assir Maintenance Office | 40452 | 41455 | 42368
90-0400 | 90-0410-20 | 160 | Abha Maintenance | 40452 | 41455 | 42368
90-0400 | 90-0415-20 | 160 | Khamis Maintenance | 40452 | 41455 | 42368
90-0400 | 90-0420-20 | 160 | Ahad Rufaidah Maintenance | 40452 | 41455 | 42368
90-0400 | 90-0430-20 | 160 | Ballasmer Maintenance | 40452 | 41455 | 42368
90-0400 | 90-0435-20 | 160 | Bisha Maintenance | 40452 | 41455 | 42368
90-0400 | 90-0440-20 | 160 | Al-Namas Maintenance | 40452 | 41455 | 42368
90-0400 | 90-0445-20 | 160 | Al Alaya Maintenance | 40452 | 41455 | 42368
90-0400 | 90-0450-20 | 160 | Tathlith Maintenance | 40452 | 41455 | 42368
90-0400 | 90-0455-20 | 160 | Tareeb Maintenance | 40452 | 41455 | 42368
90-0500 | 90-0500-00 | 160 | Jizan Maintenance Office | 40452 | 41455 | 42368
90-0500 | 90-0510-20 | 160 | Jizan Maintenance | 40452 | 41455 | 42368
90-0500 | 90-0515-20 | 160 | Sabia Maintenance old | 40452 | 41455 | 42368
90-0500 | 90-0520-20 | 160 | Samtah & Al-Khashle Maintenanc | 40452 | 41455 | 42368
90-0500 | 90-0525-20 | 160 | Abo Arish Maintenance | 40452 | 41455 | 42368
90-0500 | 90-0530-20 | 160 | Farasan Maintenance | 40452 | 41455 | 42368
90-0500 | 90-0560-20 | 160 | Emergency Group Maintenance | 40452 | 41455 | 42368
90-0500 | 90-0570-20 | 160 | Frasan Generators Maintanance | 40452 | 41455 | 42368
90-0602 | 90-0602-00 | 160 | Upgrade Power - Overhead | 41369 | 41741 | 42210
90-0602 | 90-0602-20 | 160 | Upgrade Power - Installation | 41369 | 41741 | 42210
90-0606 | 90-0606-00 | 160 | Abo Hajar - Overhead | 41122 | 41365 | 42210
90-0606 | 90-0606-10 | 160 | Abo Hajar - Procurment | 41122 | 41365 | 42210
90-0606 | 90-0606-15 | 160 | Abo Hajar - Civil Works | 41122 | 41365 | 42210
90-0606 | 90-0606-20 | 160 | Abo Hajar - Installation | 41122 | 41365 | 42210
90-0617 | 90-0617-00 | 160 | Transformers Replac King - Ove | 41131 | 41496 | 42338
90-0617 | 90-0617-20 | 160 | Transformers Replac King - Ins | 41131 | 41496 | 42338
90-0618 | 90-0618-00 | 160 | Military Industries - Overhead | 41128 | 42055 | 42420
90-0618 | 90-0618-20 | 160 | Military Industries - Install. | 41128 | 42055 | 42420
90-0623 | 90-0623-00 | 160 | Royal Air Force - Overhead | 41284 | 41649 | 42210
90-0623 | 90-0623-20 | 160 | Royal Air Force - Installation | 41284 | 41649 | 42210
90-0633 | 90-0633-00 | 160 | Over Head Line Aramco - Over H | 41730 | 42094 | 42277
90-0633 | 90-0633-20 | 160 | Over Head Line Aramco - Instal | 41730 | 42094 | 42277
90-0636 | 90-0636-00 | 160 | Abha Altaif Shifting -Overhead | 41780 | 41902 | 42215
90-0636 | 90-0636-20 | 160 | Abha Altaif Shifting -Installa | 41780 | 41902 | 42215
90-0813 | 90-0813-00 | 160 | Al-Khaldia LT Calbe - Overhead | 41518 | 41670 | 42063
90-0813 | 90-0813-20 | 160 | Al-Khaldia LT - Installation | 41518 | 41670 | 42063
90-0819 | 90-0819-00 | 160 | Al Namas Feeders - Overhead | 41609 | 41790 | 42155
90-0819 | 90-0819-20 | 160 | Al Namas Feeders-Installation | 41609 | 41790 | 42155
90-0823 | 90-0823-00 | 160 | Baladya Street Cables-Overhead | 41852 | 41973 | 42094
90-0823 | 90-0823-20 | 160 | Baladya Street Cables-Installa | 41852 | 41973 | 42094
90-0824 | 90-0824-00 | 160 | Tandaha Cable - Overhead | 41937 | 42060 | 42155
90-0824 | 90-0824-20 | 160 | Tandaha Cable - Installation | 41937 | 42060 | 42155
90-0826 | 90-0826-00 | 160 | Tandaha Cable Part2 - Overhead | 41963 | 42083 | 42185
90-0826 | 90-0826-20 | 160 | Tandaha Cable Part2 - Installa | 41963 | 42083 | 42185
90-0827 | 90-0827-00 | 160 | Al-Alaya Hospital -Overhead | 42005 | 42155 | 42247
90-0827 | 90-0827-20 | 160 | Al-Alaya Hospital - Installati | 42005 | 42155 | 42247
90-0828 | 90-0828-00 | 160 | Almarai Cable - Overhead | 42005 | 42064 | 42185
90-0828 | 90-0828-20 | 160 | Almarai Cable - Installation | 42005 | 42064 | 42185
90-0829 | 90-0829-20 | 160 | King Khalid University- Instal | 42005 | 42095 | 42247
90-0829 | 90-0829-00 | 160 | King Khalid University- Overhe | 42005 | 42095 | 42247
90-0832 | 90-0832-00 | 160 | Bisha & Shediq - Overhead | 42095 | 42216 | 42308
90-0832 | 90-0832-20 | 160 | Bisha & Shediq - Installation | 42095 | 42216 | 42308
90-0833 | 90-0833-00 | 160 | Bellasmer U/G - Overhead | 42095 | 42277 | 42369
90-0833 | 90-0833-20 | 160 | Bellasmer U/G- installation | 42095 | 42277 | 42369
90-0834 | 90-0834-00 | 160 | ALZORQ FEEDERS -Overhead | 42156 | 42247 | 42369
90-0834 | 90-0834-20 | 160 | ALZORQ FEEDERS -Installation | 42156 | 42247 | 42369
90-0902 | 90-0902-00 | 160 | OSP 2013 - Overhead | 41363 | 41973 | 42185
90-0902 | 90-0902-20 | 160 | OSP 2013 - Generator | 41363 | 41973 | 42185
90-0903 | 90-0903-00 | 160 | Replacement STC - Overhead | 41598 | 42328 | 42399
90-0903 | 90-0903-20 | 160 | Replacement STC - Installation | 41598 | 42328 | 42399
90-0983 | 90-0983-00 | 160 | Civil Work 2014 - Over Head | 41640 | 42004 | 42247
90-0983 | 90-0983-20 | 160 | Civil Work 2014 - Installation | 41640 | 42004 | 42247
90-1010 | 90-1010-00 | 160 | Mobily Riyadh - Overhead | 41001 | 41732 | 42185
90-1010 | 90-1010-20 | 160 | Mobily Riyadh - Installation | 41001 | 41732 | 42185
90-1101 | 90-1101-00 | 160 | Zain - Over Head | 41486 | 41851 | 42216
90-1101 | 90-1101-20 | 160 | Zain - Installation | 2013-07-31 | 41851 | 42216