## Master level tasks
HVCD Master Level Tasks
TASK CODE | TASK HEADS | TASK DETAILS
1 | Milestones/Overheads | Milestones/Overhead
2 | Engineering & Design | Engineering and Design
3 | Procurement | Material Procurement
4 | Civil Works | Civil Construction
5 | Installation Works | Installation
6 | Testing & Commissioning | Testing and Commissioning
7 | Project Closing | Project Closing

## Task Dictonary
HVCD Tasks List
TASK CODE | TASK NAMES (30 char) | TASK DETAILS (250 char)
1 | MILESTONE/OVERHEADS | Milestones/Overhead | 19 | OK
1.1 | Project Management Overhead | Project Management Overhead | 27 | OK
1.1.1 | OH Labor: Project Management | Project Management Overheads - Labour | 28 | OK
1.1.2 | OH NLabor: Project Management | Project Management Overheads - Non Labour | 29 | OK
1.1.3 | OH Mat: Project Management | Project Management Overheads - Material | 26 | OK
1.2 | Engineering&Design Overhead | Engineering&Design Overhead | 27 | OK
1.2.1 | OH Labor: Engineering&Design | Engineering&Design Overheads - Labour | 28 | OK
1.2.2 | OH NLabor: Engineering&Design | Engineering&Design Overheads - Non Labour | 29 | OK
1.2.3 | OH Mat: Engineering&Design | Engineering&Design Overheads - Material | 26 | OK
1.3 | Site Facilities Overhead | Site Facilities Overhead | 24 | OK
1.3.1 | OH Labor: Site Facilities | Site Facilities Overheads - Labour | 25 | OK
1.3.2 | OH Nlabor:Site Facilities | Site Facilities Overheads - Non Labour | 25 | OK
1.3.3 | OH Mat: Site Facilities | Site Facilities Overheads - Material | 23 | OK
1.4 | Installation Overhead | Installation Overhead | 21 | OK
1.4.1 | OH Labor: Installation | Installation Overherads - Labour | 22 | OK
1.4.2 | OH NLabor: Installation | Installation Overherads - Non Labour | 23 | OK
1.4.3 | OH Mat: Installation | Installation Overherads - Material | 20 | OK
2 | ENGINEERING & DESIGN | Engineering and Design | 20 | OK
2.1 | Eng&Des: UG HV CABLE | Engineering & Design for UG HV Cable | 20 | OK
2.1.1 | Eng&Des: General Design | General Design | 23 | OK
2.1.2 | Eng&Des: Electrical Design | Electrical Design | 26 | OK
2.1.3 | Eng&Des: Civil Design | Civil Design | 21 | OK
2.2 | Eng&Des: OHTL | Engineering & Design for OHTL | 13 | OK
2.2.1 | Eng&Des:110kV OHTL | Design for 110kV Double-Circuit Overhead Transmission Line | 18 | OK
2.2.2 | Eng&Des:Communication Sys/OPGW | Design for Communication System / OPGW | 30 | OK
3 | PROCUREMENT | Material Procurement | 11 | OK
3.1 | Proc: UG HV CABLE | Procurement of UG HV Cables | 17 | OK
3.1.1 | Proc: HV POWER CABLE 1200 mm2 | HV POWER CABLE 1200 mm2 | 29 | OK
3.1.2 | Proc: HV POWER CABLE 2000 mm2 | HV POWER CABLE 2500 mm2 | 29 | OK
3.1.3 | Proc: HV POWER CABLE 2500 mm2 | HV POWER CABLE 2000 mm2 | 29 | OK
3.1.4 | Proc: BONDING CABLE | BONDING CABLE | 19 | OK
3.1.5 | Proc: COAXIAL CABLE | COAXIAL CABLE | 19 | OK
3.1.6 | Proc: NFOC CABLE | NFOC CABLE | 16 | OK
3.1.7 | Proc: ALARM CABLE | ALARM CABLE | 17 | OK
3.1.8 | Proc: FOC MANAGEMENT RACK | FOC MANAGEMENT RACK | 25 | OK
3.1.9 | Proc: HV CABLE JOINT | HV CABLE JOINT | 20 | OK
3.1.10 | Proc: HV CABLE SEALING END | HV CABLE SEALING END | 26 | OK
3.1.11 | Proc: LINK BOX | LINK BOX | 14 | OK
3.1.12 | Proc: Cable Tray | Cable Tray | 16 | OK
3.1.13 | Proc: MISC. ELEC. MATERIAL | MISCELLANEOUS ELECTRICAL MATERIAL | 26 | OK
3.2 | PROC: CONSTRUCTION MATERIAL | PROCUREMENT OF CONSTRUCTION MATERIAL | 27 | OK
3.3 | PROC: OHTL MATERIAL | PROCUREMENT OF TRANSMISSION LINE MATERIAL | 20 | OK
3.3.1 | PROC: AAAC(500mm) OH Conductor | AAAC (500mm) Overhead Conductor | 30 | OK
3.3.2 | PROC: Shieldwires(OPGW) | Shieldwires (OPGW) & Accessories | 23 | OK
3.3.3 | PROC:Suspension & Tension sets | Suspension & Tension sets-Shieldwires (OPGW& OGW) | 30 | OK
3.3.4 | PROC: Latticed-steel Towers | Latticed-steel Towers | 27 | OK
3.3.5 | PROC: Insulator sets-Conductor | Insulators sets - Conductor | 30 | OK
3.3.6 | PROC: Vibration Dampers/Spacer | Vibration Dampers/Spacer | 30 | OK
3.3.7 | PROC: OPGW Cable Joint Boxes | OPGW Cable Joint Boxes | 28 | OK
4 | CIVIL WORKS | Civil Construction | 11 | OK
4.1 | Preliminary Construction | Preliminary Construction | 24 | OK
4.1.1 | Civil: Prelimini. Construction | Preliminary Construction | 30 | OK
4.1.2 | Civil: Mobilization | Mobilization for Civil Construction | 19 | OK
4.1.3 | Civil: Demolition | Demolition works | 17 | OK
4.2 | CIV: UG HV CABLE | CIVIL WORKS OF UG HV CABLES | 16 | OK
4.2.1 | CIV: Excavation | Excavation | 15 | OK
4.2.2 | CIV: Thrust Borring | Thrust Borring | 19 | OK
4.2.3 | CIV: Levelling & Compaction | Levelling & Compaction | 27 | OK
4.2.4 | CIV: Sand Bedding & Tiling | Sand Bedding & Tiling | 26 | OK
4.2.5 | CIV: Backfilling of Trench | Backfilling of Trench | 26 | OK
4.2.6 | CIV: Road Asphalt works | Road Asphalt works | 23 | OK
4.3 | FOUNDATIONS FOR OHTL TOWERS | FOUNDATIONS FOR OHTL TOWERS | 28 | OK
4.3.1 | CIV: Excavation | Excavation | 15 | OK
4.3.2 | CIV: Foundation works | Foundation works | 21 | OK
4.3.3 | CIV: Backfilling | Backfilling | 16 | OK
4.4 | CIV: CONSTRUCTION OF TUNNEL | CONSTRUCTION OF TUNNEL | 27 | OK
4.5 | CIV: ONSTRUCTION OF BUNKERS | CONSTRUCTION OF BUNKERS | 27 | OK
5 | INSTALLATION WORKS | Installation Works | 18 | OK
5.1 | INSTALLATION OF UG HV CABLE | INSTALLATION OF UG HV CABLES | 27 | OK
5.1.1 | INST: Laying of HV CABLE | Installation of HV Cable | 24 | OK
5.1.2 | INST: Termination of HV CABLE | Termination of HV Cable | 29 | OK
5.1.3 | INST: Laying of FOC CABLE | Installation of FOC Cable | 25 | OK
5.1.4 | INST: Termination of FOC CABLE | Termination of FOC Cable | 30 | OK
5.1.5 | INST: Laying of other cables | Laying of other cables | 28 | OK
5.1.6 | INST:Terminatin of other cable | Termination of other cables | 30 | OK
5.1.7 | INST: Cable interfacing(SD) | Cable interfacing during shutdown | 27 | OK
5.2 | TRANSMISSION LINE WORK | TRANSMISSION LINE WORK | 22 | OK
5.2.1 | INSTL:Erection of Steel Towers | Erection of Latticed-steel Towers | 30 | OK
5.2.2 | INSTL: Pulling of Cable | Pulling of Cable | 23 | OK
5.2.3 | INSTL: Cable Termination | Cable Termination | 24 | OK
5.2.4 | INSTL: Cable Interfacing | Cable Interfacing | 24 | OK
6 | TESTINNG & COMMISSIONING | Testing & Commissioning | 24 | OK
6.1 | T&C: 1200mm2 HV CABLE | Testinng & Commissiong of 1200mm2 HV Cable | 21 | OK
6.2 | T&C: 2000mm2 HV CABLE | Testinng & Commissiong of 2000mm2 HV Cable | 21 | OK
6.3 | T&C: 2500mm2 HV CABLE | Testinng & Commissiong of 2500mm2 HV Cable | 21 | OK
6.4 | T&C: FOC CABLE | Testinng & Commissiong of FOC Cable | 14 | OK
6.5 | T&C: OH Transmission Lines | Testinng & Commissiong of OHTL | 26 | OK
6.6 | T&C: Other cables | Testinng & Commissiong of other cables | 17 | OK
7 | PROJECT CLOSING | Project Closing | 15 | OK
7.1 | Closing: Spare Parts | Spare Parts Project Closing | 20 | OK
7.2 | Closing: Training | Training Project Closing | 17 | OK
7.3 | Closing: FAT | Factory Acceptance Test | 12 | OK
7.4 | Closing: Punch List Clearing | Punch List Clearing Project Closing | 28 | OK
7.5 | Closing: As-Built Drawings | As-Built Drawings Project Closing | 26 | OK
7.6 | Closing: De-mobilization | Demobilization | 24 | OK

## WBS Dictonary (2) (hidden)
HVCD Master Level Tasks
TASK CODE | TASK NAMES (30 char) | TASK DETAILS (250 char)
1 | Milestones / Overhead | Milestones / Overhead | 21 | OK
1.1 | Project Management Overhead | Project Management Overhead | 27 | OK
1.1.1 | OH Labor: Project Management | Project Management Overheads - Labour | 28 | OK
1.1.2 | OH NLabor: Project Management | Project Management Overheads - Non Labour | 29 | OK
1.1.3 | OH Mat: Project Management | Project Management Overheads - Material | 26 | OK
1.2 | Engineering&Design Overhead | Engineering&Design Overhead | 27 | OK
1.2.1 | OH Labor: Engineering&Design | Engineering&Design Overheads - Labour | 28 | OK
1.2.2 | OH NLabor: Engineering&Design | Engineering&Design Overheads - Non Labour | 29 | OK
1.2.3 | OH Mat: Engineering&Design | Engineering&Design Overheads - Material | 26 | OK
1.3 | Site Facilities Overhead | Site Facilities Overhead | 24 | OK
1.3.1 | OH Labor: Site Facilities | Site Facilities Overheads - Labour | 25 | OK
1.3.2 | OH Nlabor:Site Facilities | Site Facilities Overheads - Non Labour | 25 | OK
1.3.3 | OH Mat: Site Facilities | Site Facilities Overheads - Material | 23 | OK
1.4 | Installation Overhead | Installation Overhead | 21 | OK
1.4.1 | OH Labor: Installation | Installation Overherads - Labour | 22 | OK
1.4.2 | OH NLabor: Installation | Installation Overherads - Non Labour | 23 | OK
1.4.3 | OH Mat: Installation | Installation Overherads - Material | 20 | OK
2 | Engineering & Design | Engineering & Design | 20 | OK
2.1 | Eng&Des: UG HV CABLE | Engineering & Design for UG HV Cable | 20 | OK
2.1.1 | Eng&Des: General Design | General Design | 23 | OK
2.1.2 | Eng&Des: Electrical Design | Electrical Design | 26 | OK
2.1.3 | Eng&Des: Civil Design | Civil Design | 21 | OK
2.2 | Eng&Des: | Engineering & Design for TRANSMISSION LINE WORK | 10 | OK
2.2.1 | Eng&Des:110kV OHTL | Design for 110kV Double-Circuit Overhead Transmission Line | 18 | OK
2.2.2 | Eng&Des:Communication Sys/OPGW | Design for Communication System / OPGW | 30 | OK
3 | Procurement | MATERIAL / PROCUREMENT | 11 | OK
3.1 | Proc: UG HV CABLE | UG HC CABLES | 17 | OK
3.1.1 | Proc: HV POWER CABLE 1200 mm2 | HV POWER CABLE 1200 mm2 | 29 | OK
3.1.2 | Proc: HV POWER CABLE 2000 mm2 | HV POWER CABLE 2500 mm2 | 29 | OK
3.1.3 | Proc: HV POWER CABLE 2500 mm2 | HV POWER CABLE 2000 mm2 | 29 | OK
3.1.4 | Proc: BONDING CABLE | BONDING CABLE | 19 | OK
3.1.5 | Proc: COAXIAL CABLE | COAXIAL CABLE | 19 | OK
3.1.6 | Proc: NFOC CABLE | NFOC CABLE | 16 | OK
3.1.7 | Proc: ALARM CABLE | ALARM CABLE | 17 | OK
3.1.8 | Proc: FOC MANAGEMENT RACK | FOC MANAGEMENT RACK | 25 | OK
3.1.9 | Proc: HV CABLE JOINT | HV CABLE JOINT | 20 | OK
3.1.10 | Proc: HV CABLE SEALING END | HV CABLE SEALING END | 26 | OK
3.1.11 | Proc: LINK BOX | LINK BOX | 14 | OK
3.2 | Proc: MISC. ELEC. MATERIAL | Miscellaneous Elec. Material | 26 | OK
3.3 | PROC: CONSTRUCTION MATERIAL | PROCUREMENT OF CONSTRUCTION MATERIAL | 27 | OK
3.3.1 | PROC: PRECAST MANHOLES | PRECAST CONCRETE MANHOLES | 22 | OK
3.3.2 | PROC: PRECAST HANDHOLES | PRECAST CONCRETE HANDHOLES | 23 | OK
3.3.3 | PROC: SAND | SAND | 10 | OK
3.3.4 | PROC: CONCRETE FOR DUCT BANK | CONCRETE FOR DUCT BANK POURING | 28 | OK
3.3.5 | PROC: SUBBASE | SUBBASE | 13 | OK
3.3.6 | PROC: ASPHALT | ASPHALT | 13 | OK
3.3.7 | PROC: CONCRETE TILES | CONCRETE TILES | 20 | OK
3.3.8 | PROC:CABLE SUPPORT,TRAY&LADDER | CABLE SUPPORT, TRAYS & LADDERS | 30 | OK
3.4 | PROC: OHTL MATERIAL | PROCUREMENT OF TRANSMISSION LINE MATERIAL | 20 | OK
3.4.1 | PROC: AAAC(500mm) OH Conductor | AAAC (500mm) Overhead Conductor | 30 | OK
3.4.2 | PROC: Shieldwires(OPGW) | Shieldwires (OPGW) & Accessories | 23 | OK
3.4.3 | PROC:Suspension & Tension sets | Suspension & Tension sets-Shieldwires (OPGW& OGW) | 30 | OK
3.4.4 | PROC: Latticed-steel Towers | Latticed-steel Towers | 27 | OK
3.4.5 | PROC: Insulator sets-Conductor | Insulators sets - Conductor | 30 | OK
3.4.6 | PROC: Vibration Dampers/Spacer | Vibration Dampers/Spacer | 30 | OK
3.4.7 | PROC: OPGW Cable Joint Boxes | OPGW Cable Joint Boxes | 28 | OK
4 | Installation & Civil Works | Installation & Civil Works | 26 | OK
4.1 | INSTALLATION OF UG HV CABLE | INSTALLATION OF UG HV CABLES | 27 | OK
4.1.1 | INST: 1200mm2 HV CABLE | Installation of 1200mm2 HV Cable | 22 | OK
4.1.2 | INST: 2000mm2 HV CABLE | Installation of 2000m2 HV Cable | 22 | OK
4.1.3 | INST: 2500mm2 HV CABLE | Installation of 2500mm2 HV Cable | 22 | OK
4.1.4 | INST: FOC CABLE | Installation of FOC Cable | 15 | OK
4.1.5 | INST: SHUTDOWN | SHUTDOWN | 14 | OK
4.1.6 | INSTL: CONSTRUCTION OF TUNNEL | CONSTRUCTION OF TUNNEL | 29 | OK
4.1.7 | INSTL: ONSTRUCTION OF BUNKERS | CONSTRUCTION OF BUNKERS | 29 | OK
4.2 | TRANSMISSION LINE WORK | TRANSMISSION LINE WORK | 22 | OK
4.2.1 | INSTL: OHTL TOWERS FOUNDATIONS | FOUNDATIONS FOR OHTL TOWERS | 30 | OK
4.2.2 | INSTL: ELECTRICAL WORKS | ELECTRICAL WORKS | 23 | OK
5 | Testing & Commissioning | Testing & Commissioning | 23 | OK
5.1 | T&C: 1200mm2 HV CABLE | Testinng & Commissiong of 1200mm2 HV CABLE | 21 | OK
5.2 | T&C: 2000mm2 HV CABLE | Testinng & Commissiong of 2000mm2 HV CABLE | 21 | OK
5.3 | T&C: 2500mm2 HV CABLE | Testinng & Commissiong of 2500mm2 HV CABLE | 21 | OK
5.4 | T&C: FOC CABLE | Testinng & Commissiong of FOC CABLE | 14 | OK
5.4 | T&C: OH Transmission Lines | Testinng & Commissiong of OHTL | 26 | OK
6 | Project Closing | Project Closing | 15 | OK
6.1 | Closing: Spare Parts | Spare Parts Project Closing | 20 | OK
6.2 | Closing: Training | Training Project Closing | 17 | OK
6.3 | Closing: FAT | Factory Acceptance Test | 12 | OK
6.4 | Closing: Punch List Clearing | Punch List Clearing Project Closing | 28 | OK
6.5 | Closing: As-Built Drawings | As-Built Drawings Project Closing | 26 | OK
6.6 | Closing: De-mobilization | Demobilization | 24 | OK