## Major Task
Energy Project - EBU Tasks
TASK CODE | TASK HEADS | TASK DETAILS
1 | Milestones / Overhead | Milestones / Overhead
2 | Engineering & Design | Engineering & Design
3 | Procurement | Procurement
4 | Civil Construction | Civil Construction
5 | Installation | Installation
6 | Testing & Commissioning | Testing & Commissioning
7 | Project Closing | Project Closing

## Task Dictonary
Energy Project - EBU Task List
TASK CODE | TASK NAMES (30 char) | TASK DETAILS (250 char)
1 | Milestones / Overhead | Milestones / Overhead | 21 | OK
1.1 | Project Management Overhead | Project Management Overhead | 27 | OK
1.1.1 | OH Labor: Project Management | Project Management Overheads - Labour | 29 | OK
1.1.2 | OH NLabor: Project Management | Project Management Overheads - Non Labour | 30 | OK
1.1.3 | OH Mat: Project Management | Project Management Overheads - Material | 27 | OK
1.2 | Engineering&Design Overhead | Engineering&Design Overhead | 27 | OK
1.2.1 | OH Labor: Engineering&Design | Engineering&Design Overheads - Labour | 29 | OK
1.2.2 | OH NLabor: Engineering&Design | Engineering&Design Overheads - Non Labour | 30 | OK
1.2.3 | OH Mat: Engineering&Design | Engineering&Design Overheads - Material | 27 | OK
1.3 | Site Facilities Overhead | Site Facilities Overhead | 24 | OK
1.3.1 | OH Labor: Site Facilities | Site Facilities Overheads - Labour | 25 | OK
1.3.2 | OH Nlabor:Site Facilities | Site Facilities Overheads - Non Labour | 25 | OK
1.3.3 | OH Mat: Site Facilities | Site Facilities Overheads - Material | 23 | OK
1.4 | Civil Overhead | Civil Overhead | 14 | OK
1.4.1 | OH Labor: Civil | Civil Overheads - Labour | 16 | OK
1.4.2 | OH NLabor: Civil | Civil Overheads -Non Labour | 17 | OK
1.4.3 | OH Mat: Civil | Civil Overheads - Material | 14 | OK
1.5 | Lighting Overhead | Lighting Overhead | 17 | OK
1.5.1 | OH Labor: Lighting | Lighting Overheads - Labour | 19 | OK
1.5.2 | OH Nlabor: Lighting | Lighting Overheads - Non Labour | 20 | OK
1.5.3 | OH Mat: Lighting | Lighting Overheads - Material | 17 | OK
1.6 | HVAC&FF Overhead | HVAC&FF Overhead | 16 | OK
1.6.1 | OH Labor: HVAC & FF | HVAC & FF Overheads - Labour | 19 | OK
1.6.2 | OH NLabor: HVAC & FF | HVAC & FF Overheads - Non Labour | 20 | OK
1.6.3 | OH Mat: HVAC & FF | HVAC & FF Overheads - Material | 17 | OK
1.7 | Installation Overhead | Installation Overhead | 21 | OK
1.7.1 | OH Labor: Installation | Installation Overherads - Labour | 22 | OK
1.7.2 | OH NLabor: Installation | Installation Overherads - Non Labour | 23 | OK
1.7.3 | OH Mat: Installation | Installation Overherads - Material | 20 | OK
2 | Engineering & Design | Engineering & Design | 20 | OK
2.1 | Eng&Des: Electrical Sys Design | Electrical Systems Design | 30 | OK
2.2 | Eng&Des: Civil & Arch Design | Civil & Archcitecture Design | 28 | OK
2.2.1 | Eng&Des: 380kV Bldg. | 380kV Building Civil & Archcitecture Design | 21 | OK
2.2.2 | Eng&Des: HV Bldg. | 110kV or 132kV Building Civil & Archcitecture Design | 17 | OK
2.2.3 | Eng&Des: MV Bldg. | MV Bldg. Civil & Archcitecture Design | 17 | OK
2.2.4 | Eng&Des: Control Bldg. | Control Building Civil & Archcitecture Design | 22 | OK
2.3 | Eng&Des: Electro-Mech.Sys | Electro-Mechanical System Design | 26 | OK
3 | Procurement | Procurement | 11 | OK
3.1 | Procurement Electrical System | Electrical System | 29 | OK
3.1.1 | Proc: 380 kV GIS | Procurement of 380 kV GIS | 16 | OK
3.1.2 | Proc: Hybrid GIS | Procurement of 380 Hybrid GIS | 16 | OK
3.1.3 | Proc: Gantry Structures | Procurement of Gantry Structures | 23 | OK
3.1.4 | Proc: Shunt Reactor | Procurement of Shunt Reactor 380 kV | 20 | OK
3.1.5 | Proc: HV GIS | Procurement of 110 kV or 132 kV GIS | 12 | OK
3.1.6 | Proc: 33 kV Switchgear | Procurement of 33 kV Switchgear | 22 | OK
3.1.7 | Proc: 13.8 kV Switchgear | Procurement of 13.8 kV Switchgear | 24 | OK
3.1.8 | Proc: 380/HV Power Transfr. | Procurement of 380/110 kV or 132 kVPower Transformer | 27 | OK
3.1.9 | Proc: HV/33kV Power Transfr. | Procurement of 110kV or 132kV /33 kV Power Transformer | 28 | OK
3.1.10 | Proc: HV/13.8kV Power Transfr | Procurement of 110kV OR 132kV /13.8kV Power Transformer | 29 | OK
3.1.11 | Proc: MV Power Transfr | Procurement of MV Power Transformer | 22 | OK
3.1.12 | Proc: Capacitor Bank | Procurement of Capacitor Bank | 20 | OK
3.1.13 | Proc: Surge Arrestors | Procurement of Surge Arrestors | 21 | OK
3.1.14 | Proc: Auxiliary Transformer | Procurement of Auxiliary Transformer | 27 | OK
3.1.15 | Proc: NER | Procurement of NER | 10 | OK
3.1.16 | Proc: AC/DC Distribution Panel | Procurement of AC/DC Distribution Panels | 30 | OK
3.1.17 | Proc: Cable Tray & Ladder | Procurement of Cable Tray & Ladder | 25 | OK
3.1.18 | Proc: HV Cable | Procurement of 110 Kv or 132 kV Cable | 14 | OK
3.1.19 | Proc: HV Cable Sealing Ends | Procurement of 110 Kv or 132 kV Cable Sealing Ends | 27 | OK
3.1.20 | Proc: MV Cable | Procurement of MV Cable | 14 | OK
3.1.21 | Proc: MV Cable Termination | Procurement of MV Cable Termination | 26 | OK
3.1.22 | Proc: LV Cables | Procurement of LV Cables | 15 | OK
3.1.23 | Proc: Control Cable | Procurement of Control Cable | 19 | OK
3.1.24 | Proc: Batteries & Chargers | Procurement of Batteries & Chargers | 26 | OK
3.1.25 | Proc: Control&Protection Sys | Procurement of Control & Protection System | 28 | OK
3.1.26 | Proc: Trans.Fault Recorder&SOE | Procurement of Transient Fault Recorder & SOE | 30 | OK
3.1.27 | Proc: SAS System | Procurement of SAS System | 16 | OK
3.1.28 | Proc: Telecom. &SCADA System | Procurement of Telecomunication &SCADA System | 28 | OK
3.1.29 | Proc: Earthing System | Procurement of Earthing System | 21 | OK
3.1.30 | Proc: Outdoor Equipment | Procurement of Outdoor Equipment | 23 | OK
3.1.31 | Proc: Lightning&Surge Prot.Sys | Procurement of Lightning&Surge Protection System | 30 | OK
3.1.32 | Proc EM: Misc Procurement | Procurement of Miscellaneous items | 25 | OK
3.2 | Procurement Electro-Mech Sys | Procurement Electro-Mechanical System | 28 | OK
3.2.1 | Proc EM: OHTC | Procurement of Overhead Traveling Crane | 13 | OK
3.2.2 | Proc EM: HVAC System | Procurement of HVAC System | 20 | OK
3.2.3 | Proc EM Fire Fighting System | Procurement of Fire Fighting System | 28 | OK
3.2.4 | Proc EM Lighting System | Procurement of Lighting System | 23 | OK
3.2.4.1 | Proc EM: Emergency Lighting | Emergency Lighting Installation | 27 | OK
3.2.4.2 | Proc EM: Indoor Lighting | Indoor Lighting Installation | 24 | OK
3.2.4.3 | Proc EM Outdoor Lighting | Outdoor Lighting Installation | 24 | OK
4 | Civil Construction | Civil Construction | 18 | OK
4.1 | Preliminary Construction | Preliminary Construction | 24 | OK
4.1.1 | Civil: Prelimini. Construction | Preliminary Construction | 30 | OK
4.1.2 | Civil: Mobilization | Mobilization for Civil Construction | 19 | OK
4.2 | 380 kV Building | 380 kV Building | 15 | OK
4.2.1 | Civil: 380 kV GIS Basement | Civil Construction of 380 kV GIS Basement | 26 | OK
4.2.2 | Civil: 380 kV GIS Ground Floor | Civil Construction of 380 kV GIS Ground Floor | 30 | OK
4.3 | Civil: Power Transformr Fndtn | Civil Construction of Power Transformer Foundation | 29 | OK
4.4 | HV Building | 110 kV or 132 kV Building | 11 | OK
4.4.1 | Civil: HV GIS Base Constrction | 110 or 132kV Basement Construction | 30 | OK
4.4.2 | Civil: HV GIS Hall Bldg Const | 110 or 132kV GIS Hall Bldg. Construction | 29 | OK
4.5 | 33kV MV Building | MV Building | 16 | OK
4.5.1 | Civil: 33 kV Swgr Basement | Civil Construction of 33 kV Switchgear Basement | 26 | OK
4.5.2 | Civil: 33 kV Swgr Hall | Civil Construction of 33 kV Switchgear Hall | 22 | OK
4.6 | Civil: Capacitor Bank Fndtn | Civil Construction of Capacitor Bank Foundation | 27 | OK
4.7 | Civil: 13.8 kV MV SWGR Bldg | Civil Construction of 13.8 kV MV Switchgear Building | 27 | OK
4.7.1 | Civil: 13.8 kV Swgr Basement | Civil Construction of 13.8 kV Swtichgear Basement | 28 | OK
4.7.2 | Civil: 13.8 kV Swgr Hall | Civil Construction of 13.8 kV Switchgear Hall | 24 | OK
4.8 | Civil: NER foundation | Civil Construction of NER foundation | 21 | OK
4.9 | Civil Construction Contrl Bldg | Civil Construction of Control Building | 30 | OK
4.9.1 | Civil: Control Bldg Basement | Civil Construction of Control Building Basement | 28 | OK
4.9.2 | Civil: Control Bldg Grnd Floor | Civil Construction of Control Building Ground Floor | 30 | OK
4.1 | Civil: Aux. Transfor. Fndntion | Civil Construction of Auxilliary Transformer Foundation | 30 | OK
4.11 | Civil: Surge Arrester | Civil Construction of Surge Arrester | 21 | OK
4.12 | Hybrid Area 380kV / Out Door | Hybrid Area 380kV / Out Door | 29 | OK
4.12.1 | Civil: Fndntion Gantry Struc. | Civil Construction of Foundation Gantry Structure | 29 | OK
4.12.2 | Civil: Fndntin Steel Struc.GIB | Civil Construction of Foundation Steel Structure GIB | 30 | OK
4.12.3 | Civil: Fndntion 380 Hybrid GIS | Civil Construction of Foundation For 380 Hybrid GIS | 30 | OK
4.12.4 | Civil: Fndation Shunt Reactor | Civil Construction of Foundation For Shunt Reactor | 29 | OK
4.12.5 | Civil: Fencing, Bckflng&Gravel | Civil Construction of Fencing, Backfilling&Gravel Works | 30 | OK
4.13 | Civil: Cable Tunnel/Duct Banks | Civil Construction of Cable Tunnel/Duct Banks | 30 | OK
4.14 | Station Facilities | Civil Construction of Station Facilities Construction | 18 | OK
4.14.1 | Civil: Inst. Doors & Window | Civil Construction of Installation Of Doors & Window | 27 | OK
4.14.2 | Civil: Roof Deck Works | Civil Construction of Roof Deck Works | 22 | OK
4.14.3 | Civil: Intrn. Stair&Lobby Area | Civil Construction of Internal Stair Case & Lobby Area | 30 | OK
4.14.4 | Civil: Extrn. Access Staircase | Civil Construction of External Access Staircase | 30 | OK
4.14.5 | Civil: Perimeter Wall&Roadways | Civil Construction of Perimeter Wall & Roadways | 30 | OK
4.15 | CIV: COMM/BATTERY/FM-200 BLDG. | COMM / BATTERY / FM-200 BLDG. | 30 | OK
4.15.1 | CIV: FOUNDATION FOOTINGS | FOUNDATION FOOTINGS | 24 | OK
4.15.2 | CIV: COMM/BATTERY/FM-200 ROOMS | COMM. / BATTERY / FM-200 ROOMS | 30 | OK
5 | Installation | Installation | 12 | OK
5.1 | Electrical Installation | Electrical Installation | 23 | OK
5.1.1 | Instl: Cable Tray & Ladders | Installation of Cable Tray & Ladders | 27 | OK
5.1.2 | Instl: Equipment Earthing | Installation of Equipment Earthing | 25 | OK
5.1.3 | Instl: 380 Hybrid GIS | Installation of 380 Hybrid GIS | 21 | OK
5.1.4 | Instl: Shunt Reactor | Installation of Shunt Reactor 380kV | 21 | OK
5.1.5 | Instl: 380 kV GIS | Installation of 380 kV GIS | 17 | OK
5.1.6 | Instl: HV GIS | Installation of 110 kV or 132 kV GIS | 13 | OK
5.1.7 | Instl: 33 kV Switch Gear | Installation of 33 kV Switch Gear | 25 | OK
5.1.8 | Instl: 13.8 kVSwitch Gear | Installation of 13.8 kVSwitch Gear | 26 | OK
5.1.9 | Instl: Powr Transfrmer 380/ HV | Installation of Power Transformer 380/110 or 380 / 132 | 30 | OK
5.1.10 | Instl: Powr Transformer 110/33 | Installation of Power Transformer 110/33 | 30 | OK
5.1.11 | Instl: Powr Trnsfrmer 110/13.8 | Installation of Power Transformer 110/13.8 | 30 | OK
5.1.12 | Instl: Powr Transformer 132/33 | Installation of Power Transformer 132/33 | 30 | OK
5.1.13 | Instl: Powr Trnsfrmer 132/13.8 | Installation of Power Transformer 132/13.8 | 30 | OK
5.1.14 | Instl: Powr Trnsfrmer MV | Installation of Power Transformer MV | 24 | OK
5.1.15 | Instl: Outdoor Equipment | Installation of Outdoor Equipment | 24 | OK
5.1.16 | Instl: Capacitor Bank | Installation of 13.8 kV Capacitor Bank | 21 | OK
5.1.17 | Instl: Control & Protection | Installation of Control & Protection | 27 | OK
5.1.18 | Instl: SAS | Installation of Sub-Station Auto. System (SAS) | 10 | OK
5.1.19 | Instl: Telecom. &SCADA System | Installation of Telecomunication &SCADA System | 29 | OK
5.1.20 | Instl: NER | Installation of NER (13.8 kV) | 11 | OK
5.1.21 | Instl: ACDB/DCDB Panels | Installation of ACDB/DCDB Panels | 23 | OK
5.1.22 | Instl: Auxiliary Transformer | Installation of Auxiliary Transformer | 28 | OK
5.1.23 | Instl: Battery & Chargers | Installation of Battery & Chargers | 25 | OK
5.1.24 | Instl: Trnsient Falt Rcrdr&SOE | Installation of Transient Fault Recorder & SOE | 30 | OK
5.1.25 | Instl: Lightning & Protct. Sys | Installation of Lightning & Protection System | 30 | OK
5.1.26 | Instl: Steel Structures | Installation of Steel Structures | 23 | OK
5.1.27 | Instl:Remote End Works | Instalaltion of Remote End Works | 22 | OK
5.1.28 | Instl: Surge Arrestors | Installation of Surge Arrestors | 23 | OK
5.1.29 | Instl: Gantry Structures | Installation of Gantry Structures | 24 | OK
5.1.30 | Instl: HV Pwr Cble&Termination | Installation of 110kV or 132kV Power Cables & Sealing Ends | 30 | OK
5.1.31 | Instl: MV Pwer Cble&Terminatn | Installation of MV Power Cables & Termination | 29 | OK
5.1.32 | Instl: Outdoor Equipment | Installation of Outdoor Equipment | 24 | OK
5.1.33 | Instl: LV Cable&Terminatn | Installation of LV Cables | 25 | OK
5.1.34 | Instl:Control Cables&Terminatn | Installation of FOC Control Cables | 30 | OK
5.2 | Electro-Mechanical Instaltion | Electro-Mechanical Installation | 29 | OK
5.2.1 | Instl EM: OHTC | OHTC Installation | 15 | OK
5.2.2 | Inst EM: HVAC System | HVAC System Installation | 21 | OK
5.2.3 | Inst EM: FF Piping System | FF Piping System Installation | 26 | OK
5.2.4 | Inst EM: Lighting System | Lighting System Installation | 24 | OK
5.2.5 | Inst EM: Emergency Lighting | Emergency Lighting Installation | 27 | OK
5.2.6 | Inst EM: Indoor Lighting | Indoor Lighting Installation | 24 | OK
5.2.7 | Inst EM: Outdoor Lighting | Outdoor Lighting Installation | 25 | OK
5.2.8 | Inst EM: Plumbing&Waterwork | Plumbing&Waterwork Installation | 28 | OK
5.3 | Remote End Works | Remote End Works | 16 | OK
6 | Testing & Commissioning | Testing & Commissioning | 23 | OK
6.1 | T&C: 380 kV GIS | Testing & Commissioning of 380 kV GIS | 15 | OK
6.2 | T&C: Hybrid 380 GIS | Testing & Commissioning of Hybrid 380 GIS | 19 | OK
6.3 | T&C: HV GIS | Testing & Commissioning of 110 or 132kV GIS | 11 | OK
6.4 | T&C: 33 kV Switch Gear | Testing & Commissioning of 33 kV Switch Gear | 22 | OK
6.5 | T&C: 13.8 kV Switch Gear | Testing & Commissioning of 13.8 kV Switch Gear | 24 | OK
6.6 | T&C: Power Transformer 380/HV | Testing & Commissioning of Power Transformer 380/110kV or 380/132kV | 29 | OK
6.7 | T&C: Power Transformer 110/33 | Testing & Commissioning of Power Transformer 110/33 | 29 | OK
6.8 | T&C: Power Trnsformer 110/13.8 | Testing & Commissioning of Power Transformer 110/13.8 | 30 | OK
6.9 | T&C: Power Transformer 132/33 | Testing & Commissioning of Power Transformer 132/33 | 30 | OK
6.1 | T&C: Power Trnsformr 132/13.8 | Testing & Commissioning of Power Transformer 132/13.8 | 30 | OK
6.11 | T&C: 13.8 kV Capacitor Bank | Testing & Commissioning of 13.8 kV Capacitor Bank | 27 | OK
6.12 | T&C: Power And Control Cables | Testing & Commissioning of Power And Control Cables | 29 | OK
6.13 | T&C: Auxiliary Transformer | Testing & Commissioning of Auxiliary Transformer | 26 | OK
6.14 | T&C: NER | Testing & Commissioning of NER | 8 | OK
6.15 | T&C: ACDB/DCDBPanels | Testing & Commissioning of ACDB/DCDBPanels | 20 | OK
6.16 | T&C: Battery & Chargers | Testing & Commissioning of Battery & Chargers | 23 | OK
6.17 | T&C: Control & Protection | Testing & Commissioning of Control & Protection | 25 | OK
6.18 | T&C: Transient Fault Reco.&Soe | Testing & Commissioning of Transient Fault Recorder & Soe | 30 | OK
6.19 | T&C: HVAC | Testing & Commissioning of HVAC | 9 | OK
6.2 | T&C: Fire Protection Test | Testing & Commissioning of Fire Protection Test | 25 | OK
6.21 | T&C: SAS System Testing | Testing & Commissioning of SAS System Testing | 23 | OK
6.22 | T&C: SCADA&Telecom.Tests | Testing & Commissioning of SCADA&Telecommunication Tests | 24 | OK
6.23 | T&C: Close Loop & End To End | Testing & Commissioning of Close Loop & End To End | 28 | OK
7 | Project Closing | Project Closing | 15 | OK
7.1 | Closing: Spare Parts | Spare Parts Project Closing | 20 | OK
7.2 | Closing: Training | Training Project Closing | 17 | OK
7.2.1 | Training - 125 V DC System | Training - 125 V DC System | 26 | OK
7.2.2 | Training - 48 V DC System | Training - 48 V DC System | 26 | OK
7.2.3 | Training - Capacitor Bank | Training - Capacitor Bank | 25 | OK
7.2.4 | Training -Control & Protection | Training - Control & Protection | 30 | OK
7.2.5 | Training - HV GIS | Training - HV GIS | 17 | OK
7.2.6 | Training - HVAC Sytem | Training - HVAC Sytem | 21 | OK
7.2.7 | Training - MV Switch Gear | Training - MV Switch Gear | 25 | OK
7.2.8 | Training - Power Transformer | Training - Power Transformer | 28 | OK
7.2.9 | Training - SAS | Training - SAS | 14 | OK
7.2.10 | Training - Telecommunication | Training - Telecommunication | 28 | OK
7.3 | Closing: FAT | Factory Acceptance Test | 12 | OK
7.3.1 | FAT - Control & Protection | FAT - Control & Protection | 26 | OK
7.3.2 | FAT - Crane 5 Ton | FAT - Crane 5 Ton | 17 | OK
7.3.3 | FAT - HV GIS | FAT - HV GIS | 12 | OK
7.3.4 | FAT - MV Switch Gear | FAT - MV Switch Gear | 20 | OK
7.3.5 | FAT - Power Transformer | FAT - Power Transformer | 23 | OK
7.3.6 | FAT - SAS | FAT - SAS | 9 | OK
7.3.7 | FAT - Telecommunication | FAT - Telecommunication | 23 | OK
7.4 | Closing: Factory Training | Factory Training Project Closing | 25 | OK
7.5 | Closing: Site Training | Site Training Project Closing | 22 | OK
7.6 | Closing: Punch List Clearing | Punch List Clearing Project Closing | 28 | OK
7.7 | Closing: As-Built Drawings | As-Built Drawings Project Closing | 26 | OK
7.8 | Closing: De-mobilization | Demobilization | 24 | OK
7.9 | Closing: Demolition | Demolition | 19 | OK